## Project Backlog
Product Backlog
USER STORY ID | PRIORITY | AS A [type of user] | I NEED TO [do some task] | SO THAT I CAN [get some result] | ACCEPTANCE | STATUS | PRODUCT PACKLOG PRIORITY
1 | Must have | As a Project Director | get a daily report on project revenue | control and report on department revenue | Approved | Not done | Medium
2 | Must have | As a Developer | process indexed images | get information about stocks based on the analysis | Approved | Not done | High
3 | Should have | As a Developer | text recongnition on indexed images | process the extracted text | Approved | Not done | Medium
4 | Must have | As a Developer | analyze financial documents with natural language processing | process indexed web pages | Approved | Not done | Very High
5 | Must have | As a Developer | initialize blank dictionary | use its information with web crawler and update the dictionary | Approved | Not done | Very High
6 | Must have | As a Developer | extract fundamental news and reports using web crawler | update web crawler dictionary | Approved | Not done | Very High
7 | Should have | As a Developer | restart web crawler after x dictionary insertion | get more accurate results in indexed web pages | Approved | Not done | Very Low
8 | Must have | As a Developer | extract stocks' charts | use the image processing to analyzes the charts | Approved | Not done | Very High
9 | Must have | As a Developer | build a NOSQL database for web page contents | store text files and images of indexed web pages | Approved | Not done | Very High
10 | Must have | As a Developer | build a SQL database for web page indicies | map web page indicies to contents | Approved | Not done | Very High
11 | Should have | As a Developer | build a job scheduler to lunch web crawler botnet | make the botnet more organized | Approved | Not done | Low
12 | Must have | As a Customer | build a core application to use both crawler and analyzer components | provide the initial version of the profect to the customer | Approved | Not done | Very High
13 | Must have | As a Customer | build a user interface | interact with the application | Approved | Not done | High

## USER STORIES
User Story
USER STORY ID | PRIORITY | AS A [type of user] | I NEED TO [do some task] | SO THAT I CAN [get some result] | ACCEPTANCE
1 | Must have | As a Project Director | get a daily report on project revenue | control and report on department revenue | Approved
2 | Must have | As a Developer | process indexed images | get information about stocks based on the analysis | Approved
3 | Should have | As a Developer | text recongnition on indexed images | process the extracted text | Approved
4 | Must have | As a Developer | analyze financial documents with natural language processing | process indexed web pages | Approved
5 | Must have | As a Developer | initialize blank dictionary | use its information with web crawler and update the dictionary | Approved
6 | Must have | As a Developer | extract fundamental news and reports using web crawler | update web crawler dictionary | Approved
7 | Should have | As a Developer | restart web crawler after x dictionary insertion | get more accurate results in indexed web pages | Approved
8 | Must have | As a Developer | extract stocks' charts | use the image processing to analyzes the charts | Approved
9 | Must have | As a Developer | build a NOSQL database for web page contents | store text files and images of indexed web pages | Approved
10 | Must have | As a Developer | build a SQL database for web page indicies | map web page indicies to contents | Approved
11 | Should have | As a Developer | build a job scheduler to lunch web crawler botnet | make the botnet more organized | Approved
12 | Must have | As a Customer | build a core application to use both crawler and analyzer components | provide the initial version of the profect to the customer | Approved
13 | Must have | As a Customer | build a user interface | interact with the application | Approved

## PROJECT DETAILS
PROJECT NUMBER | 1
PROJECT NAME | Business Intelligence
PROJECT MANAGER | Bardia Ardakanian
DATE | 2022-01-01
VERSION | 1

## DROPDOWNS
MoSCoW
Must have
Should have
Could have
Will not have
Acceptance
Open
Pending review
Rejected
Approved
Status
Not done
Doing
Done
Rejected
Product Backlog Priority
Very High
High
Medium
Low
Very Low